## Summary
Summary
Total Test case | 50
Status | Passed | Failed | Pending | Blocked
| 16 | 13 | 16 | 5

## Test case
# | Title | Precondition | Steps | Exepected results | Priority | Autual results/ Bug | Status | Image | Notes
Login Page
TC_Login1 | Verify the user interface of login page is the same mockup |  | 1. Navigate to login page | The login page should be displayed as mock up. It means that images, control, label, color etc are properly alighed as expectation | High | Enhencement: + Person icon should be changed to Email icon + "e-mail…" and "password…" should be displayed sentence case format (Email, Password) + The "@ Education Logistics, Inc." should be added year next @ | Passed
TC_Login2 | Verify the user interface of login page is the same on all browsers |  | 1. Navigate to login page | The login page should be displayed as mock up. It means that images, control, label, color etc are properly alighed as expectation | Medium |  | Passed
TC_Login3 | Verify that user interface of login page doesn't change when resolution is changed width and height |  | 1. Navigate to login page 2. Change width and/or height from max > middle > small > smaller | The UI of login page doesn't drop/broke, size of all controls doesn't change and the scroll bar should be displayed when the screen is changed to limit of width/height | Low | The UI of page login page is broken when screen is small | Failed | Image 1
TC_Login4 | Verify that the user can move over per field when press Tab on key board |  | 1. Navigate to login page 2. Press Tab | The user can move over per field | Low |  | Passed
TC_Login5 | Verify that a user will be able to login with a valid email and password. |  | 1. Navigate to login page 2. Input valid email and password 3. Click Login | The user can login to system and Portal Parent Page is displayed | High |  | Blocked |  | Blocked by TC_Login7
TC_Login6 | Verify that a user will be able to login with a valid email, passworda and press Enter on ket board |  | 1. Navigate to login page 2. Input valid email and password 3. press Enter | The user can login to system and Portal Parent Page is displayed | Medium |  | Blocked |  | Blocked by TC_Login7
TC_Login7 | Verify that a user will NOT be able to login when miss Email and/or password |  | 1. Navigate to login page 2. Case 1 : Click Login Case 2: Input vaild Email and Click Login Case 3: Remove email, Input vaild Password and Click Login | 1. The user canNOT login to system and a error message should be displayed 2. The content of error message should correct with per case | High | Current, the user can login to system on 3 cases | Failed
TC_Login8 | Verify that a user will NOT be able to login when input a invalid data in Email and/or password |  | 1. Navigate to login page 2. Case 1 : Input a vaild Email, a invalid password and Click Login Case 2: Input a invaild Email, a valid password and Click Login Case 3: Input a invaild Email, password and Click Login | 1. The user canNOT login to system and a error message should be displayed 2. The content of error message should correct with per case | High |  | Blocked |  | Blocked by TC_Login7
TC_Login9 | Verify the data in password field is either visible as asterisk or bullet signs |  | 1. Navigate to login page 2. Input data to password | The data in password field is either visible as asterisk or bullet signs (the format of password is password type) | High |  | Passed
TC_Login10 | Verify that the system will NOT hangover when input long string and click Login |  | 1. Navigate to login page 2. Case 1 : Input a long string to Email and Click Login (max length of control) Case 2: Input a long string to Password and Click Login (max length of control) Case 3: Input a long string to Email, Password and Click Login ( max length of controll) | 1. The user cannot enter the characters more than the specified range in each field (email and Password). 2. The error message should be displayed and system will Not hang over | High |  | Blocked |  | Blocked by TC_Login7
TC_Login11 | Verify the login page allows to log in simultaneously with different credentials in a different browser. |  | 1. Navigate to login page on chrome 2. Navigate to login page on Firefox 3. Input valid email, password and click Login on 2 browser | [To Be Determine] -- Need to get requirement | Medium |  | Pending
TC_Login12 | Verify system should not allow you to enter into the system once you log out. | Login successfully to the system | 1. Click logout 2. Click back on browser | system should not allow you to enter into the system once you log out. | Medium |  | Passed
TC_Login13 | Verify the timeout functionality of the login session. | Login successfully to the system | 1. wait until timeout | [To Be Determine] -- Need to get requirement | Medium |  | Pending
TC_Login14 | Verify a user should not be allowed to log in with different credentials from the same browser at the same time. |  | 1. Open 2 tabs of chrome and login with 2 accounts | [To Be Determine] -- Need to get requirement a user should not be allowed to log in with different credentials from the same browser at the same time. | Medium |  | Pending
TC_Login15 | Verify a user should be able to login with the same credentials in different browsers at the same time. |  | 1. Open 2 browsers and login with the same account | [To Be Determine] -- Need to get requirement A user should be able to login with the same credentials in different browsers at the same time. | Medium |  | Pending
TC_Login16 | Verify that a error message should be displayed when user input incorrect format of email to email box |  | 1. Navigate to login page 2. Input invalid format of email | A error message should be displayed and content of error is correct | Medium |  | Failed
Portal Parent Page
TC_PP1 | Verify the user interface of portal parent page is the same mockup | Login successfully to the system | 1. Verify UI of page and css of link when mouse over/click | The portal parent page should be displayed as mock up. It means that images, control, label, color etc are properly alighed as expectation | High |  | Passed
TC_PP2 | Verify the user interface of portal parent page is the same on all browsers | Login successfully to the system | 1. Verify UI of page and css of link when mouse over/click | The portal parent page should be displayed as mock up. It means that images, control, label, color etc are properly alighed as expectation | Medium |  | Passed
TC_PP3 | Verify that user interface of portal parent page doesn't change when resolution is changed width and height | Login successfully to the system | 1. Change width and/or height from max > middle > small > smaller | The UI of portal parent page doesn't drop/broke, size of all controls doesn't change and the scroll bar should be displayed when the screen is changed to limit of width/height | Low | The UI of page login page is broken when screen is small | Failed | Image 2
TC_PP4 | Verify that portal parent page should be re-loaded and show current data when click [parent Portal] link | Login successfully to the system | 1. Click [parent Portal] link | The portal parent page should be refeshed and show current data on page | High |  | Pending |  | Need to get data source for compare (ex: database…)
TC_PP5 | Verify that action list should be show when click Account name | Login successfully to the system | 1. Click [Account Name] link | The Signout link should be displayed | High |  | Passed
TC_PP6 | Verify system should not allow you to enter into the system once you log out. | Login successfully to the system | 1. Click logout 2. Click back on browser | System should not allow you to enter into the system once you log out. |  |  | Passed
TC_PP7 | Verify that portal parent page should not be displayed when input URL to browser |  | 1. Open browser 2. Input http://ktvn-test.s3-website.us-east-1.amazonaws.com/ | The http://ktvn-test.s3-website.us-east-1.amazonaws.com/SignIn page should be displayed | High |  | Passed
TC_PP8 | Verify that the data of portal parent page should be refeshed when click refesh button on browser | Login successfully to the system | 1. On portal parent page: Click refesh button on browser | The portal parent page should be refeshed and show current data on page | High | Account Name is not shown | Failed | Image 3
TC_PP9 | Verify that the data is displayed correct on portal parent list/grid | Login successfully to the system | 1. Verify data on list | The data is displayed correct on portal parent list/grid | High |  | Pending |  | Need to get data source for compare (ex: database…)
Filter pop-up
TC_PP_F1 | Verify that the Filter pop-up should be displayed when Click Filter button | Login successfully to the system | 1. Click Filter button | The Filter pop-up should be displayed | High |  | Passed
TC_PP_F2 | Verify the user interface of Filter pop-up is the same mockup | Login successfully to the system | 1. Click Filter button | The Filter pop-up should be displayed as mock up. It means that images, control, label, color etc are properly alighed as expectation The data of drop down list is correct | High | Enhencement: + Student word should be removed, Name of all fields should be the same with name of column on list | Passed
TC_PP_F3 | Verify that user interface of Filter pop-up doesn't change when resolution is changed width and height | Login successfully to the system | 1. Change width and/or height from max > middle > small > smaller | The UI of pFilter pop-up doesn't drop/broke, size of all controls doesn't change and the scroll bar should be displayed when the screen is changed to limit of width/height | Low | The UI of page login page is broken when screen is small | Failed | Image 4
TC_PP_F4 | Verify that the data should be filtered correct when added a exist data on per field | Login successfully to the system | 1. Click Filter button 2. Case 1: Select per data on Request Status Case 2: Input a exist data to Email Case 3: Input a exist data to Student ID Case 4: Input a exist data to Student First Name Case 5: Input a exist data to Student Last Name 3. Click Apply Filter button | 1. A filter box should be display above list 2. The data should be filtered and displayed correct on list | High | Apply Filter function doesn't work | Failed
TC_PP_F5 | Verify that the message/comment should be displayed on list when added a un-exist data on per field | Login successfully to the system | 1. Click Filter button 2. Case 1: Input not exist data to Email Case 2: Input not exist data to Student ID Case 3: Input not exist data to Student First Name Case 4: Input not exist data to Student Last Name 3. Click Apply Filter button | 1. A filter box should be display above list 2. The message/comment should be displayed on list and content of comment is as expectation | High | Apply Filter function doesn't work | Failed
TC_PP_F6 | Verify that the data should be filtered correct when added data to many fields | Login successfully to the system | 1. Click Filter button 2. Select/ Add data to many fields 3. Click Apply Filter button Notes: Add one/many filter on one/many times | 1. The filter boxes should be display above list 2. The data should be filtered and displayed correct on list | High | Apply Filter function doesn't work | Failed
TC_PP_F7 | Verify that cancel button works | Login successfully to the system | 1. Click Filter button 2. Select/ Add data to many fields 3. Click Cancel | The data should be filtered and displayed correct on list | High | Apply Filter function doesn't work | Failed
TC_PP_F8 | Verify that data should be cleared when pop-up close | Login successfully to the system | 1. Click Filter button 2. Select/ Add data to many fields 3. Click Cancel 4. Click Filter button | The data should be cleared or return the default | High | Apply Filter function doesn't work | Failed
TC_PP_F9 | Veirfy that the filte pop-up should be hide when press esc | Login successfully to the system | 1. Click Filter button 2. Select/ Add data to many fields 3. Click Cancel 4. Press esc button | The filte pop-up should be hide | Low |  | Passed
TC_PP_F10 | Verify that the user can move over per field when press Tab on key board | Login successfully to the system | 1. Click Filter button 2. press Tab many times and check | The user can move over per field | Low |  | Passed
TC_PP_F11 | Verify that The Apply Filter function is run when press Enter | Login successfully to the system | 1. Click Filter button 2. Select/ Add data to many fields 3. Press Enter | The Apply Filter function is run The data should be filtered and displayed correct on list | Medium |  | Pending |  | Apply Filter function doesn't work
TC_PP_F12 | Verify that the data should be refeshed when click x on filter box above list | Login successfully to the system | 1. Click Filter button 2. Select/ Add data to one/many fields 3. Click Apply Filter button 4. Click x on per filter box | The filter box should be remove and the data should be reload and displayed correct on list | High |  | Pending |  | Apply Filter function doesn't work
TC_PP10 | Verify that the default column is sorted correctly | Login successfully to the system | 1. Click Filter button | The data on should be sort correct | High |  | Passed
TC_PP11 | Verify that the sort icon is displayed correct on column which allow to sort data | Login successfully to the system | 1. Click Filter button | The sort icon is displayed correct on column which allow to sort data [To Be Determine] -- Need to get requirement | High |  | Pending
TC_PP12 | Verify that data should be sorted correct when click on per name of column | Login successfully to the system | 1. Click Filter button 2. Case 1: Click Request Status Case 2: Click Request Status Case 3:Click Date Submitted Case 4:Click Date Submitted Case 5:Click Requester Case 6:Click Requester Case 7:Click First Name Case 8:Click First Name Case 9:Click Last Name Case 10:Click Last Name Case 11:Click DOB Case 12:Click DOB | Case 1,5,7,9: The data should be sorted z-a Case 2,4,8,10: The data should be sorted a-z Case 3,11: The data should be sorted current to old and "Invalid date" In end Case 4,12: The data should be sorted old to current and "Invalid date" In top | High | Sort function on case 3,11,4,12 Enhencement: + StudentID, User should be added sort function | Failed
TC_PP13 | Veirfy that Notes textbox is displayed when click on notes cell | Login successfully to the system | 1. Click on notes cell of list | The Notes textbox is displayed | High |  | Passed
TC_PP14 | Veirfy that Notes data should be saved when Click save | Login successfully to the system | 1. Click on notes cell of list 2. Input data 3. Click Save button | The data should be shown correct on list | High | The Save function doesn't work | Failed
TC_PP15 | Veirfy that the data should be limitted when input to Notes box | Login successfully to the system | 1. Click on notes cell of list 2. Input a long data 3. Click Save button | The User can not input more than max length of field | High | The Save function doesn't work | Blocked
Paging
TC_PP16 | Verify that the data should be shown correct when total item on per page is changed | Login successfully to the system System has a lot of data | 1. Change number on right-bottom of page (total item on page) 2. repeat step 1 with all items | The data should be shown correct on list | High |  | Pending |  | Not enough data to check
TC_PP17 | Verify that the data should be shown correct when Click number of page | Login successfully to the system System has a lot of data | 1. Change number on right-bottom of page (total item on page) 2. repeat step 1 with all items | The data should be shown correct on list | High |  | Pending |  | Not enough data to check
TC_PP18 | Verify that the data should be shown correct when Click > icon | Login successfully to the system System has a lot of data | 1. Click > icon 2. repeat step 1 with all pages | The Next page should be displayed and show correct data on list | High |  | Pending |  | Not enough data to check
TC_PP19 | Verify that the data should be shown correct when Click >> icon | Login successfully to the system System has a lot of data | 1. Click >> icon | The End page should be displayed and show correct data on list | High |  | Pending |  | Not enough data to check
TC_PP20 | Verify that the data should be shown correct when Click < icon | Login successfully to the system System has a lot of data | 1. Click < icon 2. repeat step 1 with all pages | The Previous page should be displayed and show correct data on list | High |  | Pending |  | Not enough data to check
TC_PP21 | Verify that the data should be shown correct when Click << icon | Login successfully to the system System has a lot of data | 1. Click << icon | The First page should be displayed and show correct data on list | High |  | Pending |  | Not enough data to check
TC_PP22 | Vefify that paging number is displayed correct on list | Login successfully to the system System has a lot of data |  | 1. Paging is hiden when the data is sort or doesn't have data 2. Paging is shown correctly when system has a lot of data | High |  | Pending |  | Not enough data to check

## Image
Image 1
Image 2
Image 3
Image 4